SAFETY FILE DOCUMENT

Risk Assessment

Terrapinn (Pty) Ltd

Sandton Convention Centre — Annual Trade Expo

| Document Ref: | IMPI-RA-2026-014 |
| --- | --- |
| Revision: | Rev 0 |
| Event Date(s): | 14 – 16 September 2026 |
| Prepared By: | S. Steynfaardt — Safety Officer (SASREA) |
| Reviewed By: | [Pending Review] |
| Approved By: | [Pending Approval] |
| Status: | DRAFT — FOR CLIENT REVIEW |

Prepared for the exclusive use of the above client. Distribution outside this scope requires written consent.

# Risk Assessment — Methodology

This risk assessment applies the A × B × C × D = R rating methodology, in line with IMPI Protection Agency's standard risk management approach and the ALARP (As Low As Reasonably Practicable) principle. A = Likelihood of occurrence, B = Severity of consequence, C = Frequency/duration of exposure, D = Number of persons potentially affected. The resulting R value determines the risk category; where practicable additional controls are applied to reduce risk to an ALARP-acceptable residual level.

| LOW (1–8) | MEDIUM (9–27) | HIGH (28–64) | EXTREME (65+) |
| --- | --- | --- | --- |

Risk Register

| No. | Activity | Hazard | Who/What May Be Harmed | Existing Controls | A | B | C | D | R | Risk Rating | Additional Controls (if required) | Res. R | ALARP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Rigging & installation of overhead trussing/branding | Falling objects / dropped tools | Riggers, exhibitors, public below | Certified rigger only; exclusion zone barricaded; daily inspection tags; tool lanyards | 3 | 4 | 2 | 3 | 72 | EXTREME | Reduce exposure window; spotter posted at exclusion zone at all times | 24 | Yes |
| 2 | Crowd movement — hall entry/exit points | Crowd crush / trip & fall | Public, exhibitors, staff | Queue barriers; trained access control staff; capacity monitoring per hall | 3 | 3 | 3 | 2 | 54 | HIGH | Add second controlled entry lane during peak (10:00–11:00) | 18 | Yes |
| 3 | Use of forklifts during build-up | Collision with pedestrians | Build-up crew, contractors | Trained/licensed operators only; horn + beacon; pedestrian walkways marked | 2 | 4 | 2 | 2 | 32 | HIGH | Banksman required during all reverse manoeuvres | 16 | Yes |
| 4 | General housekeeping — cabling, walkways | Slips, trips, falls | All persons on site | Cable covers on all walkway crossings; daily walk-through inspection | 2 | 2 | 3 | 1 | 12 | MEDIUM | N/A — controls adequate | 12 | Yes |

Sign-Off

This risk assessment has been compiled based on information provided by the client and site conditions observed/described at the time of assessment. It must be reviewed prior to each event and updated where site conditions, scope, or activities change.