SAFETY FILE DOCUMENT

Method Statement

Informa Markets

Ticketpro Dome — Trade & Industry Showcase — Rigging & Overhead Installation

| Document Ref: | IMPI-MS-2026-031 |
| --- | --- |
| Revision: | Rev 0 |
| Activity Date(s): | 02 – 04 October 2026 |
| Prepared By: | S. Steynfaardt — Safety Officer (SASREA) |
| Reviewed By: | [Pending Review] |
| Approved By: | [Pending Approval] |
| Status: | DRAFT — FOR CLIENT REVIEW |

Prepared for the exclusive use of the above client. Distribution outside this scope requires written consent.

# 1. Purpose & Scope

This method statement describes the safe system of work for rigging and overhead installation activities at the above site, and must be read in conjunction with the associated Risk Assessment (Ref: IMPI-RA-2026-031).

# 2. References

- Occupational Health and Safety Act 85 of 1993

- SASREA — Safety at Sports and Recreational Events Act 2 of 2010

- Driven Machinery Regulations, 2015

- IMPI Protection Agency Risk Assessment IMPI-RA-2026-031

# 3. Roles & Responsibilities

The Site Supervisor holds overall responsibility for this activity. All rigging work is to be carried out only by personnel holding a valid rigging certificate of competence. The IMPI Safety Officer retains authority to stop work at any time where an unsafe condition is identified.

# 4. PPE Requirements

- Hard hat (chin strap fastened at height)

- Full body harness with double lanyard — mandatory above 1.8 m

- Steel-capped safety boots

- Hi-visibility vest

- Gloves appropriate to task

# 5. Sequence of Work

| Step | Description of Task | Key Hazards & Controls | Responsible |
| --- | --- | --- | --- |
| 1 | Site establishment: erect barricading around rigging work area, display signage, brief crew on plan. | Unauthorised access — barricade full perimeter; SANS 1186-compliant signage | Site Supervisor |
| 2 | Pre-use inspection of all rigging equipment, hoists, and certified lifting gear. | Equipment failure — visual inspection + inspection tags; defective gear removed from service | Rigging Foreman |
| 3 | Lift and position overhead truss sections using certified hoists. | Falling objects — exclusion zone enforced; tag lines used; no work below suspended loads | Certified Rigger |
| 4 | Secure and tension all rigging points; verify load ratings against structural approval. | Structural failure — engineer sign-off required prior to load application | Rigging Foreman / Structural Engineer |
| 5 | Final inspection, remove barricading only once area is certified safe, handover to client. | Residual hazards — final walk-down inspection with client representative | Safety Officer |

# 6. Emergency Procedures

In the event of an incident, work stops immediately. The Site Supervisor activates the site emergency plan; first aid/medical response is coordinated via the event JOC. Emergency contact numbers are displayed at the site office and included in the Emergency Evacuation Plan for this event.

# 7. Sign-Off

This method statement is to be reviewed and signed by all personnel involved in the activity prior to commencement of work, confirming they understand and will comply with the safe system of work described above.